## Sheet2
Originating Process | No Of records in Production | Expected Delivery Date | Assigned To | Code Review | Grid/Process table | Detail | Clinic Calendar | RAD | ROC | QA Effort in Hours | Expected Completion Date
Provider Regular Schedule | 170238 | 2023-01-25 | Muthu | Rajesh | Check | Check | Check | Check | Check | 12 | 2023-01-24
Clinic Regular Schedule | 39336 | 2023-01-31 | Prabhu | Chandra | Check | Check | Check | Check | Check | 8 | 2023-01-25
Room Only Regular Schedule | 24622 | 2023-01-31 | Rajesh | Muthu | Check | Check | Check | Check | Check | 8 | 2023-01-30
Room Hold Regular Schedule |  | 2023-01-31 | Chandra | Prabhu | Check | Check | NA | Check | Check | 8 | 2023-01-31
Add Provider Clinic | 1663 | 2023-02-03 | Muthu | Rajesh | Check | NA | Check | Check | Check | 3 | 2023-02-01
Add Room Only Schedule | 34 | 2023-02-08 | Rajesh | Muthu | Check | NA | Check | Check | Check | 3 | 2023-02-01
Add Clinic | 27 | 2023-02-08 | Prabhu | Chandra | Check | NA | Check | Check | Check | 3 | 2023-02-02
Cancel Provider Clinic | 10587 | 2023-02-14 | Muthu | Rajesh | Check | NA | Check | NA | NA | 3 | 2023-02-02
Cancel Clinic | 108 | 2023-02-17 | Prabhu | Chandra | Check | NA | Check | NA | NA | 3 | 2023-02-03
Cancel Room Only Schedule | 46 | 2023-02-17 | Rajesh | Muthu | Check | NA | Check | NA | NA | 3 | 2023-02-03
Shorten Clinic | 3 |  |  |  | Check | Check | Check | Check | Check
Edit Provider Clinic | 299 |  |  |  | Check | NA | Check | Check | Check
Shorten Provider Clinic | 266 |  |  |  | Check | Check | Check | Check | Check
Limit Clinic Schedule | 34 |  |  |  | Check | NA | Check | NA | NA
Assign Provider Clinic | 3957 |  |  |  | Check | NA | Check | NA | NA
Convert Provider Clinic | 17 |  |  |  | Check | NA | Check | NA | NA
Convert Clinic |  |  |  |  | Check | NA | Check | NA | NA